|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Activity # | Activity Name | Activity Name Description | # of Days | Start Date | Dependency | Milestone |
| 1 | Meeting | Planning | 2 | 1/25/16 |  | Information about the Project |
| 2 | Create Project Team | Planning | 1 | 1/27/16 | 1 | Project Team Members |
| 3 | Create Project Schedule | Planning | 2 | 1/28/16 | 1;2 | Scheduled Project |
| 4 | Project Scope | Planning | 1 | 2/1/16 | 1;2;3 |  |
| 5 | Project Charter | Planning | 4 | 2/2/16 | 1;2;3;4 |  |
| 6 | Project Plan | Planning | 0 | 2/8/16 | 1;2;3;4;5 | Planned Project |
| 7 | Requirements Gathering | Analysis | 2 | 2/9/16 | 6 | Information about the requirements |
| 8 | Conduct Interview | Analysis | 4 | 2/11/16 | 6;7 | Interviewed Clients |
| 9 | Provide Questionnaires | Analysis | 2 | 2/18/16 | 6;7;8 | Answered Questionnaires |
| 10 | Analyze Interview/Questionnaires Result | Analysis | 8 | 2/22/16 | 6;7;8;9 | Analyzed Results |
| 11 | Draft Event Table/Use Case | Analysis | 2 | 3/4/16 | 6;7;8;9;10 | Event Table/Use Case Draft |
| 12 | Draft ERD/DD/CFD/DFD Existing | Analysis | 4 | 3/8/16 | 6;7;8;9;10;11 | ERD/DD/CFD/DFD Draft |
| 13 | Finalize Event Table and Use Case | Analysis | 5 | 3/14/16 | 6;7;8;9;10;11;12 | Final Paper of Event Table and Use Case |
| 14 | Finalize ERD/DD/CFD/DFD | Analysis | 5 | 3/21/16 | 6;7;8;9;10;11;12;13 | Final Paper of ERD/DD/DFD/CFD |
| 15 | Finalize Wiki | Analysis | 5 | 3/30/16 | 6;7;8;9;10;11;12;13;14 | Final Outputs posted in Wiki |
| 16 | Draft of GUI | Analysis | 5 | 4/6/16 | 6;7;8;9;10;11;12;13;14;15 | Development of GUI |